## Test Check to US
TEST CHECK
List of Use Story | Test case title | Overview
|  | Status | Classification of issue | Type of issue
US01 | Como programador, quero submeter o código Java do meu projeto para análise, para que o sistema possa identificar problemas e calcular métricas de qualidade. | Not tested |  |  | Status | Servertity | Issue type |  | Status | Servertity | Issue type
US02 | Como programador, quero que o sistema detete automaticamente bugs, code smells e vulnerabilidades de segurança, para que eu possa corrigir problemas críticos antes de integrar o código. | Not tested |  |  | Not tested | Urgent | Sub-Task | This is the sub-task of an issue. In a logged issue, there can be different tasks to resolve it, which are called as sub-tasks. | Not tested | Urgent | Sub-Task | This is the sub-task of an issue. In a logged issue, there can be different tasks to resolve it, which are called as sub-tasks.
US03 | Como gestor de equipa, quero visualizar diversas métricas de qualidade de cada análise, para que poder acompanhar o estado geral em que se encontra o projeto. | Not tested |  |  | In progress | High | Bug | A problem that impairs or prevents the functions of the product. | In progress | High | Bug | A problem that impairs or prevents the functions of the product.
US04 | Como gestor do projeto, quero personalizar as métricas de qualidade que vou usar e os thresholds pertencentes a cada uma, para que o projeto siga as boas práticas definidas para o desenvolvimento do código. | Not tested |  |  | Blocked | Medium | Epic | A big user story that needs to be broken down. Created by JIRA Software - do not edit or delete. | Blocked | Medium | Epic | A big user story that needs to be broken down. Created by JIRA Software - do not edit or delete.
US05 | Como gestor do projeto, quero que o sistema gere uma pontuação global da qualidade do projeto, para que eu tenha uma visão genérica e rápida do estado em que se encontra o código desenvolvido. | Not tested |  |  | Failed | Low | Improvement | An improvement or enhancement to an existing feature or task. | Failed | Low | Improvement | An improvement or enhancement to an existing feature or task.
US06 | Como gestor do projeto, quero aceder a relatórios detalhados por projeto e módulo, para que eu possa identificar rapidamente as áreas com maior número de problemas e agir de forma a adequar métodos e estratégias de desenvolvimento. | Not tested |  |  | Passed | None |  |  | Passed | None
US07 | Como gestor do projeto ou/e programador, quero comparar as diversas versões do código produzido, para que possa ver a evolução da qualidade do mesmo ao longo do tempo. | Not tested
US08 | Como gestor do projeto, quero ter a capacidade exportar relatórios em diferentes tipos (PDF, CSV ou JSON), para que possa partilhar os resultados com outras equipas ou stakeholders e até localizar aspetos a melhorar. | Not tested
US09 | Como administrador, quero ter a capacidade de visualizar dashboards interativos compostos com gráficos e outras métricas de evolução, para que possa analisar tendências e pontos críticos de forma intuitiva. | Not tested

## BURNDOWN CHART 1ºSprint
BURNDOWN CHART 1º SPRINT
Date (NOV) | Days | Goal | Done | Goal velocity | Remaining
6 | 1 | 2 | 0 | 12 | 12
7 | 2 | 2 | 0 | 10 | 12
8 | 3 | 2 | 0 | 8 | 12
9 | 4 | 2 | 0 | 6 | 12
10 | 5 | 2 | 0 | 4 | 12
11 | 6 | 2 | 0 | 2 | 12
12 | 7 | 2 | 0 | 0 | 12
Note on C8: stakeholdermap.com: Change the timescale that you need e.g. Sprint or Iteration.
Note on D8: stakeholdermap.com: Number of features of story points you plan to complete.
Note on G8: stakeholdermap.com: Number of features or story points actually remaining at the end of each day/iteration/sprint.

## BURNDOWN CHART 2ºSprint
BURNDOWN CHART 2º SPRINT
Date (NOV) | Days | Goal | Done | Goal velocity | Remaining
13 | 1 | 2 | 0 | 12 | 12
14 | 2 | 2 | 0 | 10 | 12
15 | 3 | 2 | 0 | 8 | 12
16 | 4 | 2 | 0 | 6 | 12
17 | 5 | 2 | 0 | 4 | 12
18 | 6 | 2 | 0 | 2 | 12
19 | 7 | 2 | 0 | 0 | 12
Note on C8: stakeholdermap.com: Change the timescale that you need e.g. Sprint or Iteration.
Note on D8: stakeholdermap.com: Number of features of story points you plan to complete.
Note on G8: stakeholdermap.com: Number of features or story points actually remaining at the end of each day/iteration/sprint.

## BURNDOWN CHART 3ºSprint
BURNDOWN CHART 3º SPRINT
Date (NOV) | Days | Goal | Done | Goal velocity | Remaining
20 | 1 | 2 | 0 | 12 | 12
21 | 2 | 2 | 0 | 10 | 12
22 | 3 | 2 | 0 | 8 | 12
23 | 4 | 2 | 0 | 6 | 12
24 | 5 | 2 | 0 | 4 | 12
25 | 6 | 2 | 0 | 2 | 12
26 | 7 | 2 | 0 | 0 | 12
Note on C8: stakeholdermap.com: Change the timescale that you need e.g. Sprint or Iteration.
Note on D8: stakeholdermap.com: Number of features of story points you plan to complete.
Note on G8: stakeholdermap.com: Number of features or story points actually remaining at the end of each day/iteration/sprint.

## BURNDOWN CHART 4ºSprint
BURNDOWN CHART 4º SPRINT
Date (NOV) | Days | Goal | Done | Goal velocity | Remaining
27 | 1 | 2 | 0 | 12 | 12
28 | 2 | 2 | 0 | 10 | 12
29 | 3 | 2 | 0 | 8 | 12
30 | 4 | 2 | 0 | 6 | 12
1 | 5 | 2 | 0 | 4 | 12
2 | 6 | 2 | 0 | 2 | 12
3 | 7 | 2 | 0 | 0 | 12
Note on C8: stakeholdermap.com: Change the timescale that you need e.g. Sprint or Iteration.
Note on D8: stakeholdermap.com: Number of features of story points you plan to complete.
Note on G8: stakeholdermap.com: Number of features or story points actually remaining at the end of each day/iteration/sprint.

## BURNDOWN CHART 5ºSprint
BURNDOWN CHART 5º SPRINT
Date (DEZ) | Days | Goal | Done | Goal velocity | Remaining
4 | 1 | 2 | 0 | 10 | 10
5 | 2 | 2 | 0 | 8 | 10
6 | 3 | 2 | 0 | 6 | 10
7 | 4 | 2 | 0 | 4 | 10
8 | 5 | 2 | 0 | 2 | 10
9 | 6 | 2 | 0 | 0 | 10
Note on C8: stakeholdermap.com: Change the timescale that you need e.g. Sprint or Iteration.
Note on D8: stakeholdermap.com: Number of features of story points you plan to complete.
Note on G8: stakeholdermap.com: Number of features or story points actually remaining at the end of each day/iteration/sprint.